## Business Case
Objective: Develop a business plan to sucessfully design and build ventilators within proposed budget
Phases | Deliverables | Assigned To:
Ideation | • Define clear idea of the problem we would like to solve. o Consider medical conditions and current treatment options, user needs, existing technology and go from there. • Identify and connect with all different stakeholders early in the process. o Doctors, nurses, and other medical professionals are great resources when brainstorming ideas. They live on the front lines and will be able to give you a personalized perspective of the pros and cons of current ventilation in Ethiopia. This information can be helpful in gauging need, as well. o Patients, such as friends or family members, can tell you about unpleasant experiences they may have had while being treated using ventilators in Ethiopia. Their personal stories can be especially powerful in motivating you to bring your better solution to life. | Jerusalem Darkera
Project Timeline | • Define project timeline. This should include estimates for each individual phase, not just your overall project timeline. • The amount of time you anticipate each individual phase to take matters, because different phases have different capital requirements. • Timing these phases correctly is key to managing your resources efficiently and creating an accurate budgetary estimate. Funding can also be dependent on achieving milestones, so we need to be efficient.
Budget and Cost | • Account for all expenses you might incur, plan and estimate all project costs at the beginning. • Items you may need to budget for include labor, manufacturing, materials, travel, training, consulting, product testing, regulatory compliance, and many more. • Make a realistic budget is crucial to the success of your project, and envision potential future costs. • Research regulatory pathway in Ethiopia for approval. Path to clearance or approval will have a significant impact on project timing and cost. • Research registration cost for FDA Ethiopia. There are costs involved with registering a device in different countries, in the form of paying fees, obtaining a license, or simply paying someone to oversee the registration process in Ethiopia | Sirak Takele (Lead) Keneni - supports as needed Bethel Dagim More Team Members To Join
Secure Funding | • We will need capital and a team in Ethiopia to launch product?? • Consider costs associated with manufacturing equipment, testing, certifications with notified bodies, product registrations, clinical trial management, and many other items. • Research grants, organize and manage fundraising efforts from the community
Assemble Team In Ethiopia ?? | • Act as Liason between U.S product development team and production team in Ethiopia • Research and partner up with vendors for materials, manufacturing • Form manufacturing team to execute based on design files that will be shared by U.S team???? | Mateos
Develop Regulatory Plan | • Act as a liason to work with regulatory body and Ministry of Health to develop a regulatory plan to get it cleared and out to the people. ??? | Natnael, Eden A

## Product Development Plan
Objective: Rapidly Design, Develop & Manufacture a Ventilator at Ethiopian Airlines by leveraging M.I.T open source design and predicate device, Spiro Wave Ventilator.
Product Development Process Phases | Deliverables | Description | Status | Assigned To:
Phase 1: Planning | Design & Development Plan | • Identify Scope of Project, Design & Development stages and activities • Define responsibility for Design & Development activities • Define the resources required; this includes project team members, budget as well as vendors/personnel in Ethiopia to support manunfacturing efforts • Plans should evolve throughout Design & Development |  | Jerusalem Darkera
| Product Description | Rapidly Manufactured and Low Cost Ventilators
| Quality Plan | We will comply with ISO 13485, we will bootstrap Quality Management System - Our focus will be product development (low priority)???? |  | Jerusalem Darkera
| Regulatory Plan | Regulatory agencies have defined rules that must be followed required such as ISO 13485 Design Controls. We need to comly with requirements of Ethiopian Food and Drug Administration.
| Risk Managmenent Plan | Establish A Risk Management Framework – Identify, evaluate, analyze, assess, and mitigate potential product issues. • Define Your Risk Management Process • Establish Management Roles & Responsibilities • Document Your Risk Management Plan • Establish a Living Risk Management File |  | Dr. Araya /Jerusalem
| Usability Engineering Plan | Human Factors, Usability testing, How many tests we will do? This will be covered in validation as well. Get input from Doctors. |  | Dr. Araya /Jerusalem
Phase 2: User Needs | User Requirements | • Define User Need Requirements • Define Unmet Clinical Needs that will be addressed • Define Intended Use (What is the general purpose of the medical device or its function?) • Define Indications for Use (Describe disease or condition the medical device will diagnose, treat, prevent, cure or mitigate including a description of target patient population) • Describe how your medical device is going to be used. • Establish framework of medical device product design. | Completed | Jerusalem Darkera
| System Risk Analysis (Hazard & Source Identification) | Identify potential sources of harm associated with product. Known as hazards |  | Dr. Araya /Jerusalem
Phase 3: Design Input |  | • Define Product Specifications • Establish Product Roadmap • Define Performance Criteria, requirements, and features of • your medical device product. • Note, Design Inputs should not be subjective, abstract concepts. Design Inputs should be objective and measurable. • Demonstrate that the product you develop addresses user needs
| System Risk Analysis (Hazard & Source Identification) | • Define, hazardous situations and foreseeable sequences of events • Estimate risk of each hazardous situation • Risk is the combination of severity of potential harm and probability of that harm occurring
Phase 4: Design Output | Product and Process Design Outputs (Drawings, Specifications, Work Instructions etc) | • Identify and establish design Outputs and verification methods • What sub-systems and components go into your medical device? How are these components put together? • Define materials, components, sub-assemblies, Engineering Drawings, specifications, manunfacturing instructions • Document how to assemble this product
| System Risk Evaluation | Are the risk levels acceptable, is risk reduction required? Use risk acceptability matrix as outlined in ISO 14971
Phase 5: Design Verification & Validation | Design Verification Plan & Execution | Design Verification is proving we designed correctly. Although testing is not the only way to conduct Design Verification. We might also be able to employ inspection and analysis as acceptable methods for Design Verification. • Plan Design Verification before conducting tests, inspection, • analyses. • Determine the best ways to prove Design Outputs meet Design Inputs. • Complete your Design Verification activities, document results.
| Risk Control | Use risk controls to reduce risks to acceptable levels following risk control diagram (Jerusalem will provide this)
| Residual Risk Acceptance | Evaluate risk of the product in its entirely • Is the risk level acceptable? • Do the benefits outweigh the potential risks?
| Regulatory Submission to Ethiopia FDA | Submit our documentation (Phase 1-6) to gain approval from FDA of Ethiopia, and work with regulatory agency for review
| Manufacturing Plan | Finalize manufacturing plan in preparation to design transfer (process flow raw materials, inventory, to final assemby, testing and shipping)
| Design Validation Plan and Execution | • Establish Design Validation Plan • Demonstrate that medical device meets user needs and intended use • Revisist user needs to demonstrate user needs are met • End users should be involved with design validation (doctors, nurses etc) • Document evaluation of medical device - user need should be met at this point.
| Risk Management Report | Carry out a risk management review and prepare a risk management report before sending our medical device to manufacturing. Prepare a report
Phase 6: Design Transfer | Obtain Regulatory Clearance (as necessary) | Provide our documentation (Phase 1-5) to gain approval from FDA of Ethiopia, and work with regulatory agency to gain approval
| Transfer to Manufacturing | Completing Design Transfer signifies your medical device is ready to exit product development and officially enter into production. This is significant because up until this point the “control” of the medical device has been the responsibility of the project team. Once Design Transfer occurs, the control shifts to production resources.
| Production and Post-Production Risk Management | Internal Audits, CAPAs, complaints, customer feedback and non-confirming material all feed into the risk management process - which is a total product lifecycle process.
Revisied Risk Management Report

## Deliverables
Ethiopia Covid-19 Response Team Project Name: Proj-Diy-Ventilator - To Address Shortage of Ventilators in Ethiopia by designing, developing and rapidly manufacturing low-cost ventilators.
Product Development Phases | Deliverables | Location | TImeline | Check if Completed & Documented
Planning: To identify scope of the project; define user needs and corresponding design inputs. | “Bootstrap” Quality System | Quality System |  | ☐
| Proof of Concept | Project File |  | ☐
| Research Results | Project File |  | ☐
| User Needs | Design History File |  | x
| Product Description | Project File |  | ☐
| Regulatory Strategy & Plan | Project File |  | ☐
| Design & Development Plan | Design History File |  | x
| Risk Management Plan | Risk Management File |  | x
| Project Schedule & Plan | Project File |  | x
| Funding Strategy & Plan | Project File |  | ☐
| Quality Plan | Project File |  | ☐
| Design Inputs | Design History File |  | ☐
| Design Review | Design History File |  | ☐
| Planning Phase Review | Project File |  | ☐
Design & Development: To establish product design and detailed specifications; to identify design outputs and verification methods. | Design Outputs | Design History File |  | ☐
| Risk Analysis (hazard identification) | Risk Management File |  | ☐
| Risk Evaluation | Risk Management File |  | ☐
| Risk Assessment(s) | Risk Management File |  | ☐
| Design Verification Plans | Design History File |  | ☐
| Human Factors | Project File |  | ☐
| Sales & Marketing Strategy | Project File |  | ☐
| Working Prototypes | Project File |  | ☐
| Define Regulatory Path | Project File |  | ☐
| Design Review | Design History File |  | ☐
| Design & Development Phase Review | Project File |  | ☐
Design Verification: To demonstrate the product meets the design inputs. | Design Verification Reports | Design History File |  | ☐
| Design Validation Plans | Design History File |  | ☐
| Manufacturing Plan | Project File |  | ☐
| Risk Control | Risk Management File |  | ☐
| Residual Risk Acceptance | Risk Management File |  | ☐
| Sterilization Validation (if applicable) | Design History File |  | ☐
| Software Validation (if applicable) | Design History File |  | ☐
| Design Review | Design History File |  | ☐
| Design Verification Phase Review | Project File |  | ☐
Design Validation: To demonstrate the product meets the user needs. | Regulatory Submission | Project File |  | ☐
| Revised Manufacturing Plan | Project File |  | ☐
| Design Validation Reports | Design History File |  | ☐
| IDE Clinical Trial | Project File |  | ☐
| Risk Management Report | Risk Management File |  | ☐
| Prove Market Is Receptive | Project File |  | ☐
| Prove There Are Buyers | Project File |  | ☐
| Prove Pricing Models | Project File |  | ☐
| Design Review | Design History File |  | ☐
| Design Validation Phase Review | Project File |  | ☐
Market Release: To launch product into manufacturing and marketplace. | Regulatory Clearances | Project File |  | ☐
| Reimbursement Codes | Project File |  | ☐
| Sales & Marketing Plans | Project File |  | ☐
| Production & Post-Production Risk Management | Risk Management File |  | ☐
| Revised Risk Management Report | Risk Management File |  | ☐
| Finalize Quality System | Company Quality System |  | ☐
| Transfer to Manufacturing Design Review | Design History File |  | ☐
| Market Release Phase Review | Project File |  | ☐

## Gantt Chart
Mechanical Ventilator Design Transfer to Ethiopian Airlines Schedule
PROJECT TITLE | N.E.R.D MECHANICAL VENTILATOR
PROJECT MANAGER(S) | Natnael Kebede + support
COMPANY NAME | N.E.R.D. Research Center and Ethiopia Covid-19 Response Team
DATE | 2020-04-21
[7 empty] | Milestone 1 (Phase 1-3) | [18 empty] | Milestone 2 (Phase 4-6)
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | S | D | M | T | W | R | F | S | D | M | T | W | R | F | S | D | M | T | W | R | F | S | D | M | T | W | R | F | S | D
1 | Phase 1: Planning
1.1 | Establish Design & Development Plan | Jerusalem | 2020-04-06 | 2020-04-08 | 2 | 100%
1.2 | Write Product Description | Jerusalem | 2020-04-21 | 2020-04-24 | 3 | 100%
1.3 | Establish Quality Plan |  | 2020-04-21 | 2020-04-24 | 3 | 0%
1.4 | Establish Regulatory Plan | Jerusalem |  |  |  | 0%
1.5 | Establish Risk Managmenent Plan | Dr. Araya | 2020-04-21 | 2020-04-24 | 3 | 100%
1.6 | Establish Usability Engineering Plan | Dr. Araya | 2020-04-21 | 2020-04-24 | 3 | 0%
2 | Phase 2: User Needs
2.1 | User Requirements | Jerusalem |  |  |  | 100%
2.2 | System Risk Analysis | Jerusalem/Dr.Araya/Kal |  |  |  | 0%
3 | Phase 3: Design Inputs
3.1 | Demonstrate product specification addresses user needs | Jerusalem and Dr. Eros | 2020-04-21 | 2020-04-24 | 3 | 95%
3.2 | Finalize Risk Management Plan and System Risk Analysis | Dr. Araya | 2020-04-21 | 2020-04-24 |  | 0%
4 | Phase 4: Design Outputs
4.1 | Identify and establish design outputs and verification methods | Binyam and N.E.R.D | 2020-04-25 |  | -43946 | 0%
4.2 | Define materials, components, sub-assemblies, Engineering Drawings, specifications, manunfacturing instructions | Gobena, Binyam, N.E.R.D | 2020-04-25 |  | -43946 | 30%
4.3 | Document how to assemble this product |  | 2020-04-25 |  | -43946 | 0%
5 | Phase 5: Verification and Validation
5.1 | Plan design verification before conducting tests & inspection |  | 2020-04-27 |  |  | 0%
5.2 | Write test plans for functionality, reliability and usability testing | Jerusalem/Dr. Araya/ Dr. Eros | 2020-04-28 | 2020-04-29 |  | 0%
5.3 | Perform functionality, reliability and usability testing | N.E.R.D | 2020-04-30 |  |  | 0%
5.4 | Document test results | N.E.R.D | 2020-05-01 |  |  | 0%
5.5 | Establish validation plan (Do design output meets design inputs?) | Dr. Araya/Jerusalem/Dr.Eros/Kal | 2020-05-01 |  |  | 0%
5.6 | Use risk controls to reduce risks to acceptable levels following risk control diagram | Dr. Araya/Jerusalem/Dr.Eros/ Kal | 2020-05-01 |  |  | 0%
Establish Manufacturing Process Flow (raw materials inventory to final assembly, test and shipping)
6 | Phase 6: Design Transfer
6.1 | Conduct a comprehensive Design Review |  | 2020-05-04 |  |  | 0%
6.2 | Prepare FDA submission for approval to manufacturing |  | 2020-05-05 |  |  | 0%
6.3 | Transfer Design to Manufacturing |  | 2020-05-07 |  |  | 0%
0%
0%

## Volunteers
Roles | Responsibilities | Team Members | Location | Vounteer Sign-up
Health Professionals
Doctors, Nurses, Hospital Professionals | Act as advisors to help formulate user needs. Also involved during design validation phase. |  | Ethiopia
Non-Technical Roles
Project Coordinator - Doc Control and Traceability |  |  | Anywhere
Project Manager - Project Timeline | Ensures we follow timeline for each phase | Nardos | Anywhere
Budget Manager | Budget , production cost | Sirak, Keneni | Anywhere
Resource Management | Resource management (materials research etc) | Dagim Sisay and Nathnael | Ethiopia
Copy Writer for User Manual | Write guides, instructions for use (amharic, english etc) |  | Anywhere
Technical Roles
Materials Engineers | Advise on materials sections, properties |  | Anywhere
Manufacturing Engineers | Supply Chain Experience preferred in medical device, automotive or aerospace industries |  | Ethiopia - preferred.. Anywhere
Software Engineer | Human machine interface skills; experienced with embedded systems as well |  | Ethiopia - preferred.. Anywhere
Electrical Engineers | (three levels: Schematic designs, PCB layout, software)
Mechanical Engineers | Fluid machine design, Pneumatic system Design and testing | Binyam Minassie, Salem | Ethiopia - preferred.. Anywhere
Biomedical Engineers | Systems Engineering Risk Management (hazard, risk mitigation) Human Factors User Need Product Specification Quality and Regulatory Professionals (lead FDA approval process and QMS) | Fesseha Atlaw Ezirg Ymer Wolle Dr. Araya Amsalu, Jerusalem Darkera, Kalkidan Zewdu Zenebe Abebe | Anywhere (Regulatory Expertise from Ethiopia needed)